## Slide 1
TMI-2 CAP Meeting
Date: September 14, 2022
Time: 6:00pm – 7:30pm Location: Virtual via Microsoft Teams, accessible through
www.tmi2solutions.com
Dial In: +1 385-500-4880
With Conference ID 612222219#

## Slide 2: Welcome & Attendance
Steve Letavic
Chairman, TMI-2 Community Advisory Panel

## Slide 3: Agenda
Decommissioning Status
Regulatory Update
Preservation & Outreach
PADEP Bureau of Radiation Protection
Nuclear Regulatory Commission
CAP Business & Open Discussion
Community Q&A

## Slide 4: Decommissioning Status
Frank Helin
TMI-2 Project Director

## Slide 5
Project Performance
Overall Assessment
  Safety performance remains very good
  Team remains focused on planning and program readiness including technology assessments
  Schedule and budget performance very good
Challenges/Risks
  Obtaining additional Emergency Plan update and approval for decommissioning (DECON)
  NRC approval of DECON License Amendment Request (LAR) expected by January 2023
  Incorporating an early aggressive dose reduction approach to sequencing work

## Slide 6: Safety Performance
Safety performance remains very good, with some minor occurrences:
  Worker became weak during respirator testing and fell, injuring an elbow
  Worker slipped on debris in truck and strained a hamstring
  Worker tripped in a clean (non-contaminated) area which aggravated a pre-existing condition; individual requested an ambulance and received care upon reaching the ER
Weekly safety stand down meetings now occurring to ensure focus remains on safe work practices

## Slide 7: Project Highlights
Shifting procedures and processes from TMI-1 to ESJ
  Radiological Protection Program
  Fire Protection Program
  Engineering
TMI-2 Materials Security Plan implemented (30 August 2022)
  Using TMI-1 support under contract
Performing in-depth surveys of Reactor Building, Auxiliary Building, and Fuel Handling Building to finalize plans to address source term reduction
  Focusing on protection of personnel and minimizing radiological risk

## Slide 8: Critical Path
Critical path for active decommissioning (DECON) depends on the NRC approval of the DECON License Amendment Request (LAR)
  Currently addressing NRC Requests for Additional Information (RAIs)
  Working on addressing TMI Site Emergency Plan revision to support entry into DECON
  Expect NRC approval by end of 2022 / beginning of 2023
Preparations for entering active decommissioning in early 2023
  Removal of Equipment Hatch
  Design and construction of Decommissioning Support Building (DSB) and Interim Waste Storage Facility (IWSF)

## Slide 9: Project Focus Areas
Current Project Work
  Designing a structure to support material handling (DSB)
  Dose reduction efforts
  Programs on track to implement DECON LAR when approved with multiple readiness reviews being performed
Continue to work closely with Constellation/TMI-1 on:
  Support Services (e.g., Security)
  Combined Site Wide programs (e.g., environmental monitoring)
  TMI Site Emergency Plan

## Slide 10: Project Focus Areas
Staffing
  Obtaining needed staff onsite for support and operations
    RP technicians for ongoing Reactor Building surveys
    Currently 8 craft labor personnel which will grow to 52 by mid-October
      ESJ uses 100% craft labor from local union halls, except when specialty labor is needed
Dose Reduction
  Reviewing advances in technological methods to perform remote work with minimal risk for exposure to personnel
Program transfers from Constellation
  Radiological Protection – complete
  Security – complete
  Other programs scheduled for transition in 2023

## Slide 11: Regulatory Update
Timothy Devik
Licensing Manager, TMI-2

## Slide 12: Overview
PDMS to DECON License Amendment Request (LAR) Status
TMI-2 Security LAR Status
Emergency Plan LAR Status
Records Exemption Status
NRC Inspection Status
Searching on NRC ADAMS

## Slide 13: PDMS to DECON License Amendment Request (LAR) Status
Original Submitted February 2021
Working through NRC Requests for Additional Information (RAIs)
  Fire analysis bases
  Special Nuclear Material accountability and control
Emergency Plan update to account for TMI-2 Decontamination activities
Target for NRC approval is end of 2022

## Slide 14: TMI-2 Security License Amendment Request (LAR) Status
Original submittal May 2021
License Amendment approved on 30 August 2022
Implemented TMI-2 Materials Security Plan under contract with TMI-1 to provide services
Coordinated implementation with TMI-1 implementation of ISFSI Security Plan and with TMI-1 Materials Security Plan

## Slide 15: Emergency Plan License Amendment Request (LAR) Status
ISFSI-only Emergency Plan submitted for TMI site March 2021
PADEP noted that Emergency Plan assumed TMI-2 would remain in Post-Defueling Monitored Storage (PDMS) condition
  TMI-2 revising Emergency Plan for DECON condition to support DECON LAR
  TMI-2 will remain in PDMS condition until DECON LAR approval, with DECON Emergency Plan implemented
Coordinating Emergency Plan update with TMI-1 and NRC

## Slide 16: Records Exemption Status
TMI-2 Solutions requested an exemption from some of the NRC record keeping requirements for the life of the license on 5 October 2021
  Eliminate requirements for abandoned equipment
  Supplemented in December 2021 to address NRC Orders regarding maintenance TMI-2 accident records
  Specific Code of Federal Regulations records requirements:
    10 CFR 50, Appendix B, Criterion XVII
    10 CFR 50.59(d)(3)
    10 CFR 50.71(c)
NRC is expected to approve the exemption in the coming weeks

## Slide 17: NRC Inspection Status
NRC Inspection Activities 12-15 September 2022
  TMI-2 Radiation Protection Program Inspection
  TMI-2 Materials Security Program Inspection (10 CFR Part 37)
NRC Management Visit, 12-15 September 2022
  Site familiarization

## Slide 18: Receive Links for Public Documents for TMI-2 via Email
Go to www.nrc.gov
Select Public Meetings and Involvement
Select Subscribe to Email Updates
Scroll down to Lyris Subscription Services
  Click the link to the Decommissioning and Uranium Recovery Correspondence page
Add your name and email address and select Three Mile Island Station, Unit 2 -5000320 (Middletown, PA)
  As items are put on the docket, you will get an email notification

## Slide 19: Preservation Efforts & Outreach
Hannah Pell
TMI-2 Licensing Engineer

## Slide 20: TMI-2 Historic Preservation
Finalized TMI-2 Historic Resource Survey Form (HRSF) draft update with environmental contractors
  SHPO reviewing and providing comments
  Cultural Resources Protection Plan development to align with HRSF update
Will continue to maintain historical records regarding the TMI-2 accident in 1979 after Records Exemption approval

## Slide 21: TMI Charity Golf Tournament
18th year of the tournament
Approx. 120 golfers participated in the event w/ 13 volunteers
Approx. 30 industry vendors sponsored golfers or donated
Raised $30,000 for Londonderry Volunteer Fire Co.

## Slide 23: PADEP Bureau of Radiation Protection
Dwight A. Shearer, P.E.
Director, Bureau of Radiation Protection

## Slide 24: NRC Reactor Decommissioning Licensing Three Mile Island Station, Unit 2 Community Advisory Panel - Virtual
Amy M. Snyder
Senior Project Manager
U.S. Nuclear Regulatory Commission
14 September 22

## Slide 25: Licensing Actions
Amendment Issued:
TMI-2- Amendment No. 65 (ML22189A194 PKG)
  Physical Security Plan
  (May 13, 2021, ADAMS Accession No. ML21144A262 (non-public) as supplemented on September 21, 2021 (ML21267A505), March 31 (ML22102A304), April 28 (ML22125A013), May 3 (non-public), May 9 (non-public), and May 10, 2022 (ML22131A138)
Amendment Under Review:
  Change of License from Possession Only to DECON and change of Technical Specifications
  February 21, 2021, ADAMS Package Accession No. ML21057A047, as supplemented on May 5, 2021 (ML21133A264), January 7, 2022 (ML22013A177), March 23, 2022 (ML22101A079), April 7, 2022 (ML22101A077), and May 16, 2022 (ML22138A285)

## Slide 26: Licensing Actions
Exemption:
TMI-2- Decommissioning Record Keeping
  Request for Exemption from Record Retention Requirements
  October 5, 2021 (ADAMS Accession No. ML21279A278, as supplemented, on December 15, 2021 (ML21354A027))

## Slide 27: Future Licensing Submittals
  Emergency Preparedness Plan – Emergency Action Level Changes - to be submitted TBD

## Slide 28: Site Visits Week of September 12
  Physical Security Inspection
  Site Familiarization visit- NRC HQ staff
    Meet and greet
    Tour
    Decommissioning plans
    Environmental Program
    Radiological Protection Program

## Slide 29: Questions and Contact Information
  Questions on Presentation?
  Contact Information:
    Amy Snyder, Senior Project Manager
    Amy.Snyder@nrc.gov
    301 415-6822

## Slide 30: CAP Business & Open Discussion
Steve Letavic
Chairman, TMI-2 Community Advisory Panel

## Slide 31
Community Q&A
Please contact Hannah Pell at hepell@energysolutions.com
with any additional questions or requests for information.